## Read Me
Joint Deployment and Distribution Enterprise
Pass 24 reference model · damaged-theater entry, force closure and sustainment · FY2026 planning dollars
Decision view
Question | Reference answer |  |  | Campaign | Reference | Degraded
What is being built? | A permanent National Resilience Deployment and Distribution Enterprise under Strategic Mobility Command—not a logistics adjunct. |  |  | C1 | 1.4482 | 1.231
What changes from Pass 23? | Deployment is time-phased into anticipatory, 72-hour service, 14-day initial capability, 45-day force closure and 90-day depth. |  |  | C2 | 1.2285 | 1.0443
What closes? | All ten reference campaigns close across movement, reception, onward movement, responder basing and daily sustainment under declared assumptions. |  |  | C3 | 1.0924 | 0.76465
What remains fragile? | A correlated primary-entry-path loss breaks the Cascadia and allied megacity campaigns; eight of ten degraded chains close. |  |  | M1 | 1.1325 | 1.0362
What does it cost? | The attributable enterprise envelope is a decomposition of Pass 23—not additive to it—and includes formation, fixed-network, R&D, workforce, digital and industrial lines. |  |  | M2 | 1.0259 | 1.0054
Rendering status | Blocked. The asset classes are planning equivalents until engineering configurations and evidence gates close. |  |  | M3 | 1.1893 | 1.0109
|  |  |  | M4 | 1.2423 | 1.056
|  |  |  | M5 | 1.439 | 1.2231
Reader path |  |  |  | G1 | 1.0933 | 0.76533
Sequence | Read | Decision |  | G2 | 1.0692 | 1.0158
1 | Campaigns → Wave Doctrine → Campaign Waves | Separate life-safety initiation from full force closure.
2 | Mode Assignment → Movement Fleet → Movement Capacity | Test whether national lift closes by mode and deadline.
3 | Entry Node Classes → Campaign Nodes → Reception | Test damaged-theater entry and correlated loss.
4 | Onward → Responder Bases → Sustainment → End-to-End | Expose the weakest link in each campaign chain.
5 | Force Structure → Asset Build → Prepared Network → Workforce | See what must exist before the emergency.
6 | Capital Crosswalk → Annual Funding → Operating Cost | Reconcile this enterprise to the Pass 23 force and fiscal architecture.
7 | Innovation Portfolio → Authority Gates → Evidence Gates → Checks | See what must be invented, governed and proven.
Headline outputs
Metric | Value | Unit | Meaning
Reference campaign chains closed | 10 | of 10 | Every required link has margin ≥ 1.0
Degraded campaign chains closed | 8 | of 10 | Correlated loss case; not a probability
Full deployed mass | 11.5807 | million t | Same ten-campaign force as Pass 23
Attributable capital envelope | 4.7441 | $T | Inside the $12.049T Pass 23 total
Affiliated enterprise workforce | 1.2079 | million billet-eq. | Direct plus allocated institutional overhead
Mature annual operating screen | 332.5491 | $B/year | Crosswalk, not incremental appropriations

## Controls
Controls
Editable policy and planning assumptions; blue type on pale tan cells. These are hypotheses, not validated performance.
Variable | Reference | Unit | Interpretation
Reference campaign count | 10 | campaigns | 3 catastrophic + 5 major + 2 global
Initial operating capability deadline | 14 | days | R0 + R1 + R2 mass received and cleared
Force-closure deadline | 45 | days | R0 through R3 mass in theater
Depth deadline | 90 | days | All deployable mass and replacement depth
Responder base modules per opening command | 8 | modules | Modular sites, not one giant camp
People per base module | 8250 | people | Zero-host-utility designed capacity
Base module availability | 80% | share | Material, crew and movement availability
Gross onward throughput per sustainment command | 18000 | t/day | Before availability and route factors
Onward availability | 82% | share | Command, vehicles, hubs and communications
Gross sustainment throughput per command | 8000 | t/day | Daily replenishment and reverse flow
Formation O&M rate | 3% | share of capital/year | Screening rate only
Common enabling O&M rate | 2% | share of capital/year | Fixed network, research and industrial lines
Institutional overhead | 12% | share of direct billets | Allocated from Pass 23, not additive
Program reserve | 20% | share of pre-reserve capital | Pass 23 policy reserve
Annual personnel-cost assumptions
Component | $B per billet-equivalent | $K equivalent | Boundary
Permanent federal | 0.00016 | 160 | Compensation, benefits and ordinary support
Federal reserve | 5e-05 | 50 | Paid readiness, training and mobilization average
State / territorial | 5.5e-05 | 55 | Combined planning equivalent
Certified industry | 9e-05 | 90 | Readiness retainer and mobilizable labor
Partner / allied | 2e-05 | 20 | U.S. exercise and access support only

## Campaigns
Campaign Set
The Pass 23 ten-campaign force translated into movement, entry and sustainment demand.
ID | Class | Reference campaign | Theater | Duration d | Deployed people | Deployable mass t | Supply t/day | Opening commands | Sustainment commands | Forecast lead d | Onset
C1 | Catastrophic | Continental grid failure during temperature extreme | Domestic / continental | 180 | 58510 | 996800 | 12230 | 2 | 3 | 0 | systemic
C2 | Catastrophic | Sequential Gulf–Atlantic hurricane | Domestic / coastal | 180 | 83600 | 1345600 | 17335 | 3 | 4 | 5 | forecast
C3 | Catastrophic | Cascadia earthquake and tsunami | Domestic / coastal | 240 | 108110 | 1762600 | 22520 | 4 | 5 | 0 | no-notice
M1 | Major | Western wildfire–heat–smoke complex | Domestic / west | 90 | 41960 | 646100 | 8475 | 1 | 2 | 3 | forecast
M2 | Major | Urban heat emergency | Domestic / metro | 45 | 45210 | 725100 | 9145 | 1 | 2 | 4 | forecast
M3 | Major | Inland flood | Domestic / inland | 120 | 57230 | 984600 | 12195 | 2 | 3 | 3 | forecast
M4 | Major | Regional tornado sequence | Domestic / inland | 60 | 64070 | 1065600 | 13465 | 2 | 3 | 0 | no-notice
M5 | Major | Territorial drought and water emergency | Territorial / island | 180 | 56280 | 899100 | 11625 | 2 | 3 | 10 | slow-onset
G1 | Global | Allied coastal megacity earthquake | International / coastal | 180 | 99430 | 1573600 | 20400 | 3 | 4 | 0 | no-notice
G2 | Global | Regional flood and displacement mission | International / regional | 180 | 100090 | 1581600 | 20860 | 3 | 4 | 3 | forecast
Portfolio totals
Measure | Value | Unit | Interpretation
Simultaneous deployed people | 714490 | people | Before rotation and institutional force
Deployable mass | 11580700 | t | Full formation mass
Daily sustainment | 148250 | t/day | Formation supply screen
Opening commands | 23 | formations | J-TOC simultaneous demand
Sustainment commands | 33 | formations | J-TSC simultaneous demand

## Wave Doctrine
Deployment Wave Doctrine
A service-effect timeline prevents early life safety from being confused with full equipment closure.
Band | Name | Timing | Cumulative deadline d | Closure criterion | Boundary
R0 | Anticipatory | -120 h to event | 0 | Stage reversible packages outside the impact zone | Only forecastable campaigns receive credit
R1 | Minimum viable service | 0–72 h | 3 | Command, access, life safety, medical continuity, communications | Initiates bounded service; not force closure
R2 | Initial operating capability | Day 4–14 | 14 | Stable entry network and first utility / health / hazard effects | Reception and onward movement are binding
R3 | Force closure | Day 15–45 | 45 | Complete operating formations and responder bases in theater | Main sealift, rail and construction wave
R4 | Depth and endurance | Day 46–90 | 90 | Replacement, stock depth, redundant routes and reconstitution | No early-life-safety credit
Rules
Rule | Meaning
Public effect precedes formation closure | Small integrated packages may begin care, access, communications and command while heavy systems are still moving.
No equipment-only credit | A wave closes only when people, authority, communications, receiving capacity, support and output measurement arrive together.
Anticipation is conditional | R0 is credited only where forecast lead and reversible safe-zone staging exist.
Mass is not value | Movement priority is set by avoided harm and service dependency, not tonnes or platform visibility.

## Campaign Waves
Campaign Wave Demand
Fifty time-phased demand records; fractions are editable and must reconcile to 100% by campaign.
Campaign | Reference campaign | Band | Wave | Mass share | Cumulative share | Full mass t | Wave mass t | Deadline d | Public-effect meaning
C1 | Continental grid failure during temperature extreme | R0 | Anticipatory | 2% | 2% | 996800 | 19936 | 0 | Stage reversible packages outside the impact zone
C1 | Continental grid failure during temperature extreme | R1 | Minimum viable service | 6% | 8% | 996800 | 59808 | 3 | Command, access, life safety, medical continuity, communications
C1 | Continental grid failure during temperature extreme | R2 | Initial operating capability | 22% | 30% | 996800 | 219296 | 14 | Stable entry network and first utility / health / hazard effects
C1 | Continental grid failure during temperature extreme | R3 | Force closure | 45% | 75% | 996800 | 448560 | 45 | Complete operating formations and responder bases in theater
C1 | Continental grid failure during temperature extreme | R4 | Depth and endurance | 25% | 100% | 996800 | 249200 | 90 | Replacement, stock depth, redundant routes and reconstitution
C2 | Sequential Gulf–Atlantic hurricane | R0 | Anticipatory | 12% | 12% | 1345600 | 161472 | 0 | Stage reversible packages outside the impact zone
C2 | Sequential Gulf–Atlantic hurricane | R1 | Minimum viable service | 8% | 20% | 1345600 | 107648 | 3 | Command, access, life safety, medical continuity, communications
C2 | Sequential Gulf–Atlantic hurricane | R2 | Initial operating capability | 25% | 45% | 1345600 | 336400 | 14 | Stable entry network and first utility / health / hazard effects
C2 | Sequential Gulf–Atlantic hurricane | R3 | Force closure | 40% | 85% | 1345600 | 538240 | 45 | Complete operating formations and responder bases in theater
C2 | Sequential Gulf–Atlantic hurricane | R4 | Depth and endurance | 15% | 100% | 1345600 | 201840 | 90 | Replacement, stock depth, redundant routes and reconstitution
C3 | Cascadia earthquake and tsunami | R0 | Anticipatory | 0% | 0% | 1762600 | 0 | 0 | Stage reversible packages outside the impact zone
C3 | Cascadia earthquake and tsunami | R1 | Minimum viable service | 5% | 5% | 1762600 | 88130 | 3 | Command, access, life safety, medical continuity, communications
C3 | Cascadia earthquake and tsunami | R2 | Initial operating capability | 18% | 23% | 1762600 | 317268 | 14 | Stable entry network and first utility / health / hazard effects
C3 | Cascadia earthquake and tsunami | R3 | Force closure | 47% | 70% | 1762600 | 828422 | 45 | Complete operating formations and responder bases in theater
C3 | Cascadia earthquake and tsunami | R4 | Depth and endurance | 30% | 100% | 1762600 | 528780 | 90 | Replacement, stock depth, redundant routes and reconstitution
M1 | Western wildfire–heat–smoke complex | R0 | Anticipatory | 10% | 10% | 646100 | 64610 | 0 | Stage reversible packages outside the impact zone
M1 | Western wildfire–heat–smoke complex | R1 | Minimum viable service | 12% | 22% | 646100 | 77532 | 3 | Command, access, life safety, medical continuity, communications
M1 | Western wildfire–heat–smoke complex | R2 | Initial operating capability | 28% | 50% | 646100 | 180908 | 14 | Stable entry network and first utility / health / hazard effects
M1 | Western wildfire–heat–smoke complex | R3 | Force closure | 35% | 85% | 646100 | 226135 | 45 | Complete operating formations and responder bases in theater
M1 | Western wildfire–heat–smoke complex | R4 | Depth and endurance | 15% | 100% | 646100 | 96915 | 90 | Replacement, stock depth, redundant routes and reconstitution
M2 | Urban heat emergency | R0 | Anticipatory | 8% | 8% | 725100 | 58008 | 0 | Stage reversible packages outside the impact zone
M2 | Urban heat emergency | R1 | Minimum viable service | 12% | 20% | 725100 | 87012 | 3 | Command, access, life safety, medical continuity, communications
M2 | Urban heat emergency | R2 | Initial operating capability | 30% | 50% | 725100 | 217530 | 14 | Stable entry network and first utility / health / hazard effects
M2 | Urban heat emergency | R3 | Force closure | 35% | 85% | 725100 | 253785 | 45 | Complete operating formations and responder bases in theater
M2 | Urban heat emergency | R4 | Depth and endurance | 15% | 100% | 725100 | 108765 | 90 | Replacement, stock depth, redundant routes and reconstitution
M3 | Inland flood | R0 | Anticipatory | 8% | 8% | 984600 | 78768 | 0 | Stage reversible packages outside the impact zone
M3 | Inland flood | R1 | Minimum viable service | 10% | 18% | 984600 | 98460 | 3 | Command, access, life safety, medical continuity, communications
M3 | Inland flood | R2 | Initial operating capability | 27% | 45% | 984600 | 265842 | 14 | Stable entry network and first utility / health / hazard effects
M3 | Inland flood | R3 | Force closure | 40% | 85% | 984600 | 393840 | 45 | Complete operating formations and responder bases in theater
M3 | Inland flood | R4 | Depth and endurance | 15% | 100% | 984600 | 147690 | 90 | Replacement, stock depth, redundant routes and reconstitution
M4 | Regional tornado sequence | R0 | Anticipatory | 0% | 0% | 1065600 | 0 | 0 | Stage reversible packages outside the impact zone
M4 | Regional tornado sequence | R1 | Minimum viable service | 10% | 10% | 1065600 | 106560 | 3 | Command, access, life safety, medical continuity, communications
M4 | Regional tornado sequence | R2 | Initial operating capability | 25% | 35% | 1065600 | 266400 | 14 | Stable entry network and first utility / health / hazard effects
M4 | Regional tornado sequence | R3 | Force closure | 45% | 80% | 1065600 | 479520 | 45 | Complete operating formations and responder bases in theater
M4 | Regional tornado sequence | R4 | Depth and endurance | 20% | 100% | 1065600 | 213120 | 90 | Replacement, stock depth, redundant routes and reconstitution
M5 | Territorial drought and water emergency | R0 | Anticipatory | 5% | 5% | 899100 | 44955 | 0 | Stage reversible packages outside the impact zone
M5 | Territorial drought and water emergency | R1 | Minimum viable service | 4% | 9% | 899100 | 35964 | 3 | Command, access, life safety, medical continuity, communications
M5 | Territorial drought and water emergency | R2 | Initial operating capability | 16% | 25% | 899100 | 143856 | 14 | Stable entry network and first utility / health / hazard effects
M5 | Territorial drought and water emergency | R3 | Force closure | 40% | 65% | 899100 | 359640 | 45 | Complete operating formations and responder bases in theater
M5 | Territorial drought and water emergency | R4 | Depth and endurance | 35% | 100% | 899100 | 314685 | 90 | Replacement, stock depth, redundant routes and reconstitution
G1 | Allied coastal megacity earthquake | R0 | Anticipatory | 0% | 0% | 1573600 | 0 | 0 | Stage reversible packages outside the impact zone
G1 | Allied coastal megacity earthquake | R1 | Minimum viable service | 4% | 4% | 1573600 | 62944 | 3 | Command, access, life safety, medical continuity, communications
G1 | Allied coastal megacity earthquake | R2 | Initial operating capability | 16% | 20% | 1573600 | 251776 | 14 | Stable entry network and first utility / health / hazard effects
G1 | Allied coastal megacity earthquake | R3 | Force closure | 45% | 65% | 1573600 | 708120 | 45 | Complete operating formations and responder bases in theater
G1 | Allied coastal megacity earthquake | R4 | Depth and endurance | 35% | 100% | 1573600 | 550760 | 90 | Replacement, stock depth, redundant routes and reconstitution
G2 | Regional flood and displacement mission | R0 | Anticipatory | 2% | 2% | 1581600 | 31632 | 0 | Stage reversible packages outside the impact zone
G2 | Regional flood and displacement mission | R1 | Minimum viable service | 5% | 7% | 1581600 | 79080 | 3 | Command, access, life safety, medical continuity, communications
G2 | Regional flood and displacement mission | R2 | Initial operating capability | 18% | 25% | 1581600 | 284688 | 14 | Stable entry network and first utility / health / hazard effects
G2 | Regional flood and displacement mission | R3 | Force closure | 45% | 70% | 1581600 | 711720 | 45 | Complete operating formations and responder bases in theater
G2 | Regional flood and displacement mission | R4 | Depth and endurance | 30% | 100% | 1581600 | 474480 | 90 | Replacement, stock depth, redundant routes and reconstitution

## Mode Assignment
Strategic Mode Assignment
Full-mass routing hypothesis by campaign. Actual time-phased load plans must be item-level.
Campaign | Air | Ocean | Land / rail | Inland water | Share check | Design logic
C1 | 8% | 0% | 82% | 10% | 100% | Continental surface network with air urgency and waterway relief
C2 | 8% | 45% | 35% | 12% | 100% | Coastal access plus forecastable surface staging
C3 | 10% | 50% | 25% | 15% | 100% | Damaged coast requires ocean, littoral and inland alternatives
M1 | 12% | 0% | 83% | 5% | 100% | Distributed western surface and air response
M2 | 15% | 0% | 85% | 0% | 100% | Metro air urgency but primarily surface-delivered support
M3 | 8% | 5% | 55% | 32% | 100% | Inland water is a maneuver route, not only a hazard
M4 | 12% | 0% | 80% | 8% | 100% | Distributed road / rail network with urgent air packages
M5 | 8% | 65% | 12% | 15% | 100% | Island and territorial endurance depends on maritime movement
G1 | 10% | 75% | 5% | 10% | 100% | Intercontinental heavy movement is maritime
G2 | 8% | 60% | 10% | 22% | 100% | Regional water access diversifies ocean entry

## Movement Fleet
Strategic Movement Fleet
Purpose-built transport equivalents. Payload, availability, cycle and cost are design assumptions pending configurations.
ID | Mode | Asset class | Force owner | Inventory | Payload t | Availability | Cycles/day | Activation d | Unit capital $B | Effective t/day | Boundary
F01 | Air | Long-range heavy lifter | A-SMW | 464 | 100 | 75% | 0.6 | 0.5 | 0.45 | 20880 | Urgent intercontinental modules; payload-equivalent assumption
F02 | Air | Medium short-field strategic lifter | A-SMW | 696 | 35 | 75% | 1 | 0.5 | 0.18 | 18270 | Austere air access and regional movement
F03 | Air | Autonomous heavy cargo aircraft | A-SMW | 2320 | 8 | 65% | 1.2 | 0.5 | 0.035 | 14476.8 | Novel capability; technical and safety gates remain open
F04 | Ocean | Strategic response RO/RO | M-SSG | 142 | 25000 | 80% | 0.05 | 4 | 3 | 142000 | Purpose-built mission cargo and self-sustaining discharge
F05 | Ocean | Fast response logistics ship | M-SSG | 71 | 12000 | 80% | 0.083333 | 3 | 2 | 56799.7728 | Speed prioritizes closure over commercial efficiency
F06 | Land / rail | Resilience rail mission set | J-TSC | 204 | 3500 | 80% | 0.33333 | 1 | 0.1 | 190399.8096 | Locomotive, rolling stock, loading and repair package
F07 | Land / rail | Heavy highway convoy set | J-TSC | 510 | 1000 | 80% | 0.5 | 1 | 0.03 | 204000 | Fifty-vehicle equivalent with maintenance and drivers
F08 | Inland water | Modular barge train | M-IWG | 216 | 4000 | 75% | 0.25 | 2 | 0.18 | 162000 | Push boat, barges, ramp and handling system
F09 | Inland water | Shallow workboat / ferry set | M-IWG | 108 | 300 | 75% | 0.5 | 1 | 0.2 | 12150 | Local crossing and break-bulk movement

## Movement Capacity
Movement Capacity by Deadline
National portfolio capacity by mode. Preposition credit is bounded; transport capacity accrues only after activation.
Mode | Full demand t | Due by 72h | Due by 14d | Due by 45d | Due by 90d | Preposition t | Effective t/day | Activation d | 72h capacity | 14d capacity | 45d capacity | 90d capacity | 72h status | 14d status | 45d status | 90d status
Air | 1112405 | 15% | 60% | 95% | 100% | 75000 | 53626.8 | 0.5 | 209067 | 798961.8 | 2461392.6 | 4874598.6 | PASS | PASS | PASS | PASS
Ocean | 4249625 | 3% | 25% | 85% | 100% | 150000 | 198799.7728 | 4 | 150000 | 2137997.728 | 8300790.6848 | 17246780.4608 | PASS | PASS | PASS | PASS
Land / rail | 4620326 | 12% | 55% | 90% | 100% | 250000 | 394399.8096 | 1 | 1038799.6192 | 5377197.5248 | 17603591.6224 | 35351583.0544 | PASS | PASS | PASS | PASS
Inland water | 1598344 | 3% | 40% | 85% | 100% | 75000 | 174150 | 2 | 249150 | 2164800 | 7563450 | 15400200 | PASS | PASS | PASS | PASS

## Entry Node Classes
Entry Node Classes
Fixed and mobile reception capacity. Effective throughput is theoretical throughput × force availability before campaign damage.
ID | Node class | Inventory | Gross t/day | Availability | Effective t/day | Complete capability | Unit capital $B | Capital owner
NREC | Prepared Resilience Entry Complex | 24 | 45000 | 90% | 40500 | Multi-modal anchor outside direct impact; paired with alternate | 10 | Prepared network
AEG | Expeditionary Air Entry Group | 67 | 1500 | 75% | 1125 | Airfield assessment, repair, ATC, fuel, cargo and rescue | 2.5 | A-AAG
POG | Expeditionary Port Opening Group | 60 | 12000 | 68% | 8160 | Hydrography, clearance, salvage, cranes and control | 3 | M-POG
LAG | Littoral Entry Group | 69 | 6000 | 68% | 4080 | Damaged-quay, beach and shallow-water transfer | 2 | M-LAG
IWG | Inland Water Entry Group | 54 | 8000 | 68% | 5440 | River / lake terminal, ferry and distribution | 1.5 | M-IWG
LRG | Land / Rail Entry Group | 121 | 6000 | 74% | 4440 | Route assessment, bridge access, railhead and terminal control | 1.2 | L-ROG

## Campaign Nodes
Campaign Entry Architecture
Allocated fixed and mobile node equivalents for the ten simultaneous campaigns.
Campaign | NREC | Air | Port | Littoral | Inland | Land / rail | Reference damage factor | Primary-path-loss factor | Base access factor | Architecture
C1 | 2 | 2 | 0 | 0 | 2 | 10 | 80% | 70% | 85% | Continental paired surface corridors
C2 | 3 | 3 | 5 | 5 | 2 | 8 | 75% | 65% | 85% | Forecast permits safe-zone staging; coast remains damaged
C3 | 2 | 5 | 6 | 8 | 2 | 8 | 55% | 20% | 70% | Severe correlated port, road and utility loss
M1 | 2 | 3 | 0 | 0 | 1 | 7 | 85% | 75% | 90% | Distributed western entry
M2 | 2 | 3 | 0 | 0 | 0 | 6 | 90% | 80% | 90% | Metro access with prepared complexes
M3 | 2 | 2 | 1 | 2 | 6 | 7 | 80% | 70% | 85% | Waterways supplement damaged roads
M4 | 2 | 3 | 0 | 0 | 2 | 8 | 80% | 70% | 85% | Many small damage clusters require distributed nodes
M5 | 1 | 2 | 4 | 4 | 3 | 4 | 75% | 65% | 85% | Territorial maritime bridge with one prepared anchor
G1 | 0 | 5 | 8 | 9 | 2 | 8 | 65% | 22% | 70% | No U.S. fixed complex; partner access and mobile opening only
G2 | 0 | 5 | 7 | 9 | 5 | 8 | 65% | 55% | 80% | Multiple sovereign nodes and inland-water routes
Inventory reconciliation
Node class | Allocated | Inventory | Availability-credit inventory | Status
Prepared Resilience Entry Complex | 16 | 24 | 21.6 | PASS
Expeditionary Air Entry Group | 33 | 67 | 50.25 | PASS
Expeditionary Port Opening Group | 31 | 60 | 40.8 | PASS
Littoral Entry Group | 37 | 69 | 46.92 | PASS
Inland Water Entry Group | 25 | 54 | 36.72 | PASS
Land / Rail Entry Group | 74 | 121 | 89.54 | PASS

## Reception
Damaged-Theater Reception
Fourteen-day initial operating capability. Capacity is the weighted entry portfolio after campaign damage.
Campaign | Required t/day | Theoretical node t/day | Reference damage | Reference capacity | Reference margin | Primary-loss factor | Degraded capacity | Degraded margin | Reference | Degraded
C1 | 21360 | 138530 | 80% | 110824 | 5.1884 | 70% | 77576.8 | 3.6319 | PASS | PASS
C2 | 43251.4286 | 232475 | 75% | 174356.25 | 4.0312 | 65% | 113331.5625 | 2.6203 | PASS | PASS
C3 | 28957 | 214625 | 55% | 118043.75 | 4.0765 | 20% | 23608.75 | 0.8153 | PASS | FAIL
M1 | 23075 | 120895 | 85% | 102760.75 | 4.4533 | 75% | 77070.5625 | 3.34 | PASS | PASS
M2 | 25896.4286 | 111015 | 90% | 99913.5 | 3.8582 | 80% | 79930.8 | 3.0866 | PASS | PASS
M3 | 31647.8571 | 163290 | 80% | 130632 | 4.1277 | 70% | 91442.4 | 2.8894 | PASS | PASS
M4 | 26640 | 130775 | 80% | 104620 | 3.9272 | 70% | 73234 | 2.749 | PASS | PASS
M5 | 16055.3571 | 125790 | 75% | 94342.5 | 5.8761 | 65% | 61322.625 | 3.8194 | PASS | PASS
G1 | 22480 | 154025 | 65% | 100116.25 | 4.4536 | 22% | 22025.575 | 0.97979 | PASS | FAIL
G2 | 28242.8571 | 162185 | 65% | 105420.25 | 3.7326 | 55% | 57981.1375 | 2.0529 | PASS | PASS

## Onward
Staging and Onward Movement
Theater throughput from entry node to operating location. Port clearance without onward capacity is not reception.
Campaign | Required t/day | J-TSC allocated | Gross per command | Availability | Reference route factor | Reference capacity | Reference margin | Degraded route factor | Degraded capacity | Degraded margin | Reference | Degraded
C1 | 21360 | 3 | 18000 | 82% | 85% | 37638 | 1.7621 | 85% | 31992.3 | 1.4978 | PASS | PASS
C2 | 43251.4286 | 4 | 18000 | 82% | 90% | 53136 | 1.2285 | 85% | 45165.6 | 1.0443 | PASS | PASS
C3 | 28957 | 5 | 18000 | 82% | 75% | 55350 | 1.9115 | 70% | 38745 | 1.338 | PASS | PASS
M1 | 23075 | 2 | 18000 | 82% | 90% | 26568 | 1.1514 | 90% | 23911.2 | 1.0362 | PASS | PASS
M2 | 25896.4286 | 2 | 18000 | 82% | 90% | 26568 | 1.0259 | 98% | 26036.64 | 1.0054 | PASS | PASS
M3 | 31647.8571 | 3 | 18000 | 82% | 85% | 37638 | 1.1893 | 85% | 31992.3 | 1.0109 | PASS | PASS
M4 | 26640 | 3 | 18000 | 82% | 85% | 37638 | 1.4128 | 85% | 31992.3 | 1.2009 | PASS | PASS
M5 | 16055.3571 | 3 | 18000 | 82% | 85% | 37638 | 2.3443 | 85% | 31992.3 | 1.9926 | PASS | PASS
G1 | 22480 | 4 | 18000 | 82% | 85% | 50184 | 2.2324 | 70% | 35128.8 | 1.5627 | PASS | PASS
G2 | 28242.8571 | 4 | 18000 | 82% | 85% | 50184 | 1.7769 | 80% | 40147.2 | 1.4215 | PASS | PASS

## Responder Bases
Responder Basing
Self-sufficient living and work capacity protects responders and prevents the force from consuming damaged host utilities.
Campaign | Deployed people | Opening commands | Modules / command | People / module | Availability | Reference access | Reference capacity | Reference margin | Degraded access | Degraded capacity | Degraded margin | Reference | Degraded
C1 | 58510 | 2 | 8 | 8250 | 80% | 85% | 89760 | 1.5341 | 83.3% | 87964.8 | 1.5034 | PASS | PASS
C2 | 83600 | 3 | 8 | 8250 | 80% | 85% | 134640 | 1.6105 | 83.3% | 131947.2 | 1.5783 | PASS | PASS
C3 | 108110 | 4 | 8 | 8250 | 80% | 70% | 147840 | 1.3675 | 49% | 103488 | 0.95725 | PASS | FAIL
M1 | 41960 | 1 | 8 | 8250 | 80% | 90% | 47520 | 1.1325 | 88.2% | 46569.6 | 1.1099 | PASS | PASS
M2 | 45210 | 1 | 8 | 8250 | 80% | 90% | 47520 | 1.0511 | 88.2% | 46569.6 | 1.0301 | PASS | PASS
M3 | 57230 | 2 | 8 | 8250 | 80% | 85% | 89760 | 1.5684 | 83.3% | 87964.8 | 1.537 | PASS | PASS
M4 | 64070 | 2 | 8 | 8250 | 80% | 85% | 89760 | 1.401 | 83.3% | 87964.8 | 1.3729 | PASS | PASS
M5 | 56280 | 2 | 8 | 8250 | 80% | 85% | 89760 | 1.5949 | 83.3% | 87964.8 | 1.563 | PASS | PASS
G1 | 99430 | 3 | 8 | 8250 | 80% | 70% | 110880 | 1.1152 | 49% | 77616 | 0.78061 | PASS | FAIL
G2 | 100090 | 3 | 8 | 8250 | 80% | 80% | 126720 | 1.2661 | 78.4% | 124185.6 | 1.2407 | PASS | PASS

## Sustainment
Sustainment and Reverse Flow
Daily supply capacity must include water, food, fuel, medical, repair, waste, casualties and returned equipment.
Campaign | Required t/day | J-TSC allocated | Gross per command | Availability | Reference route factor | Reference capacity | Reference margin | Degraded route factor | Degraded capacity | Degraded margin | Reference | Degraded
C1 | 12230 | 3 | 8000 | 82% | 90% | 17712 | 1.4482 | 85% | 15055.2 | 1.231 | PASS | PASS
C2 | 17335 | 4 | 8000 | 82% | 90% | 23616 | 1.3623 | 85% | 20073.6 | 1.158 | PASS | PASS
C3 | 22520 | 5 | 8000 | 82% | 75% | 24600 | 1.0924 | 70% | 17220 | 0.76465 | PASS | FAIL
M1 | 8475 | 2 | 8000 | 82% | 90% | 11808 | 1.3933 | 90% | 10627.2 | 1.2539 | PASS | PASS
M2 | 9145 | 2 | 8000 | 82% | 90% | 11808 | 1.2912 | 90% | 10627.2 | 1.1621 | PASS | PASS
M3 | 12195 | 3 | 8000 | 82% | 85% | 16728 | 1.3717 | 85% | 14218.8 | 1.166 | PASS | PASS
M4 | 13465 | 3 | 8000 | 82% | 85% | 16728 | 1.2423 | 85% | 14218.8 | 1.056 | PASS | PASS
M5 | 11625 | 3 | 8000 | 82% | 85% | 16728 | 1.439 | 85% | 14218.8 | 1.2231 | PASS | PASS
G1 | 20400 | 4 | 8000 | 82% | 85% | 22304 | 1.0933 | 70% | 15612.8 | 0.76533 | PASS | FAIL
G2 | 20860 | 4 | 8000 | 82% | 85% | 22304 | 1.0692 | 95% | 21188.8 | 1.0158 | PASS | PASS

## End-to-End
End-to-End Campaign Closure
A campaign closes only at its weakest required link. Ratios are capacities divided by declared demand.
Campaign | Reception | Onward | Responder base | Sustainment | Reference minimum | Binding reference link | Reference | Reception degraded | Onward degraded | Base degraded | Sustainment degraded | Degraded minimum | Degraded
C1 | 5.1884 | 1.7621 | 1.5341 | 1.4482 | 1.4482 | Sustainment | PASS | 3.6319 | 1.4978 | 1.5034 | 1.231 | 1.231 | PASS
C2 | 4.0312 | 1.2285 | 1.6105 | 1.3623 | 1.2285 | Onward | PASS | 2.6203 | 1.0443 | 1.5783 | 1.158 | 1.0443 | PASS
C3 | 4.0765 | 1.9115 | 1.3675 | 1.0924 | 1.0924 | Sustainment | PASS | 0.8153 | 1.338 | 0.95725 | 0.76465 | 0.76465 | FAIL
M1 | 4.4533 | 1.1514 | 1.1325 | 1.3933 | 1.1325 | Responder base | PASS | 3.34 | 1.0362 | 1.1099 | 1.2539 | 1.0362 | PASS
M2 | 3.8582 | 1.0259 | 1.0511 | 1.2912 | 1.0259 | Onward | PASS | 3.0866 | 1.0054 | 1.0301 | 1.1621 | 1.0054 | PASS
M3 | 4.1277 | 1.1893 | 1.5684 | 1.3717 | 1.1893 | Onward | PASS | 2.8894 | 1.0109 | 1.537 | 1.166 | 1.0109 | PASS
M4 | 3.9272 | 1.4128 | 1.401 | 1.2423 | 1.2423 | Sustainment | PASS | 2.749 | 1.2009 | 1.3729 | 1.056 | 1.056 | PASS
M5 | 5.8761 | 2.3443 | 1.5949 | 1.439 | 1.439 | Sustainment | PASS | 3.8194 | 1.9926 | 1.563 | 1.2231 | 1.2231 | PASS
G1 | 4.4536 | 2.2324 | 1.1152 | 1.0933 | 1.0933 | Sustainment | PASS | 0.97979 | 1.5627 | 0.78061 | 0.76533 | 0.76533 | FAIL
G2 | 3.7326 | 1.7769 | 1.2661 | 1.0692 | 1.0692 | Sustainment | PASS | 2.0529 | 1.4215 | 1.2407 | 1.0158 | 1.0158 | PASS

## Degraded Case
Correlated Primary-Path-Loss Case
Deterministic design stress: the largest entry path and connected host services are lost together. This is not a probability estimate.
Campaign | Reference minimum | Degraded minimum | Loss of margin | Degraded status | Interpretation
C1 | 1.4482 | 1.231 | 0.21724 | PASS | Continental alternates preserve closure
C2 | 1.2285 | 1.0443 | 0.18428 | PASS | Forecast staging preserves closure
C3 | 1.0924 | 0.76465 | 0.32771 | FAIL | Pacific Northwest corridor and base redundancy insufficient
M1 | 1.1325 | 1.0362 | 0.096269 | PASS | Distributed paths preserve closure
M2 | 1.0259 | 1.0054 | 0.020519 | PASS | Prepared metro access preserves closure
M3 | 1.1893 | 1.0109 | 0.17839 | PASS | Waterway alternatives preserve closure
M4 | 1.2423 | 1.056 | 0.18635 | PASS | Distributed terminals preserve closure
M5 | 1.439 | 1.2231 | 0.21585 | PASS | Maritime bridge retains margin
G1 | 1.0933 | 0.76533 | 0.328 | FAIL | Partner-node and responder-base depth insufficient
G2 | 1.0692 | 1.0158 | 0.053461 | PASS | Multinode regional architecture preserves closure

## Force Structure
Deployment Enterprise Force Structure
Eleven Pass 23 formation families constitute the standing entry, movement and sustainment enterprise.
WBS | Formation | Inventory | Direct billets | Pass 23 capital $B | Role in chain
A-SMW | Strategic mobility wing | 58 | 156600 | 464 | Strategic air movement
A-AAG | Austere air-access group | 67 | 70350 | 167.5 | Open damaged and austere airfields
A-TDG | Tactical distribution group | 108 | 145800 | 324 | Hub-to-need movement
M-POG | Port-opening group | 60 | 81000 | 180 | Open and operate damaged ports
M-LAG | Littoral-access group | 69 | 72450 | 138 | Bridge ship-to-shore and damaged quays
M-IWG | Inland-waterway group | 54 | 40500 | 81 | Use rivers and lakes as access corridors
M-OSG | Offshore-support group | 45 | 94500 | 315 | Afloat repair, stores and responder support
M-SSG | Ocean sustainment group | 71 | 138450 | 639 | Strategic sealift, replenishment and retrograde
L-ROG | Access and route-opening group | 121 | 110110 | 145.2 | Open roads, bridges and rail corridors
J-TOC | Theater-opening command | 36 | 54000 | 43.2 | Integrate entry, authority, effects and responder bases
J-TSC | Theater sustainment command | 51 | 114750 | 76.5 | Control onward movement, sustainment and reverse flow
Reconciliation
Measure | Value | Unit | Boundary
Formation families | 11 | lines | Subset of 34 Pass 23 families
Direct billets | 1078510 | billet-equivalents | Before allocated institutional overhead
Formation capital | 2573.4 | $B | Inside Pass 23 non-NUPS formation acquisition

## Asset Build
Purpose-Built Asset Build
Illustrative platform and system quantities allocated to the eleven formation budgets. No rendering or configuration claim.
Source WBS | Asset / system class | Quantity | Unit capital $B | Extended capital $B | Operational function
A-SMW | Long-range heavy lifter | 464 | 0.45 | 208.8 | Urgent strategic air
A-SMW | Medium short-field strategic lifter | 696 | 0.18 | 125.28 | Austere and regional air
A-SMW | Autonomous heavy cargo aircraft | 2320 | 0.035 | 81.2 | Novel distributed air movement
A-SMW | Wing maintenance / loading system | 58 | 0.84 | 48.72 | Depot, loading and readiness package
A-AAG | Airfield opening core | 67 | 1 | 67 | Assessment, command and airfield operations
A-AAG | Runway repair / ATC / fuel set | 134 | 0.5 | 67 | Two sets per group
A-AAG | Air cargo / rescue set | 67 | 0.5 | 33.5 | Handling, rescue and quick-turn maintenance
A-TDG | Tactical cargo aircraft | 648 | 0.22 | 142.56 | Short-field hub-to-need
A-TDG | Vertical heavy lifter | 864 | 0.15 | 129.6 | Precision access without intact runway
A-TDG | Uncrewed cargo craft | 2160 | 0.024 | 51.84 | Last-100-km recurring movement
M-POG | Port opening system | 60 | 1.5 | 90 | Survey, clearance, salvage and command
M-POG | Heavy cargo handling set | 120 | 0.4 | 48 | Cranes, reach stackers and power
M-POG | Dredging / hydrographic set | 60 | 0.7 | 42 | Channel, berth and obstruction recovery
M-LAG | Shallow landing connector | 276 | 0.25 | 69 | Four per group
M-LAG | Modular causeway system | 138 | 0.3 | 41.4 | Two per group
M-LAG | Beach / damaged-quay interface pack | 69 | 0.4 | 27.6 | One per group
M-IWG | Modular barge train | 216 | 0.18 | 38.88 | Four per group
M-IWG | Shallow workboat / ferry set | 108 | 0.2 | 21.6 | Two per group
M-IWG | River terminal set | 54 | 0.38 | 20.52 | One per group
M-OSG | Offshore support ship | 45 | 4 | 180 | Afloat stores, workshops and responder support
M-OSG | Afloat repair / medical / base package | 45 | 2 | 90 | Modular mission package
M-OSG | Utility craft | 90 | 0.5 | 45 | Two per group
M-SSG | Strategic response RO/RO | 142 | 3 | 426 | Two per group
M-SSG | Fast response logistics ship | 71 | 2 | 142 | One per group
M-SSG | Fleet support / replenishment package | 71 | 1 | 71 | One per group
L-ROG | Route-opening train | 121 | 0.55 | 66.55 | Survey, clearance and surface repair
L-ROG | Modular crossing set | 242 | 0.15 | 36.3 | Two per group
L-ROG | Traffic / bridge assessment pack | 121 | 0.15 | 18.15 | One per group
L-ROG | Autonomous earthmoving fleet | 121 | 0.2 | 24.2 | Novel high-tempo repair capability
J-TOC | Command / sensing / interoperability core | 36 | 0.5 | 18 | One per command
J-TOC | Entry-control node | 72 | 0.2 | 14.4 | Two per command
J-TOC | Authority / service-integration pack | 36 | 0.3 | 10.8 | One per command
J-TSC | Theater distribution control node | 51 | 0.3 | 15.3 | One per command
J-TSC | Forward distribution hub | 102 | 0.2 | 20.4 | Two per command
J-TSC | Resilience rail mission set | 204 | 0.1 | 20.4 | Four per command
J-TSC | Heavy highway convoy set | 510 | 0.03 | 15.3 | Ten per command
J-TSC | Reverse-flow / reconstitution pack | 51 | 0.1 | 5.1 | One per command

## Prepared Network
Prepared National Entry Network
Permanent peacetime infrastructure makes crisis entry fast. Archetype counts are not siting recommendations.
ID | Network element | Quantity | Unit capital $B | Extended $B | Design boundary
N01 | Prepared Resilience Entry Complex | 24 | 10 | 240 | Paired multimodal nodes outside direct impact; no city siting claim
N02 | Dispersed auxiliary airfield / terminal | 48 | 3 | 144 | Pre-surveyed, hardened interfaces and stored opening kits
N03 | Inland distribution campus | 72 | 1.5 | 108 | Rail, road, water, cold chain, repair and reverse logistics
N04 | Responder base campus | 60 | 1.8 | 108 | Zero-host-utility lodging, sanitation, medical and crew recovery
Network doctrine
Principle | Requirement
Paired entry | Every anchor has a geographically and infrastructurally independent alternate
Safe-zone geometry | Primary reception and responder bases sit outside the modeled correlated impact zone
Daily use | Ports, yards, airfields, colleges and depots sustain workforce and industrial demand between crises
No host draw | Base modules bring water, energy, sanitation, communications, food and waste systems
Reverse logistics | Casualties, contaminated waste, damaged equipment, containers and recovered assets have planned return paths

## Workforce
Workforce Crosswalk
Component billets are copied from Pass 23 formation lines; institutional overhead is allocated, not added to the department total.
WBS | Permanent federal | Federal reserve | State / territorial | Certified industry | Partner / allied | Direct total
A-SMW | 101790 | 39150 | 7830 | 7830 | 0 | 156600
A-AAG | 45727.5 | 17587.5 | 3517.5 | 3517.5 | 0 | 70350
A-TDG | 94770 | 36450 | 7290 | 7290 | 0 | 145800
M-POG | 56700 | 16200 | 1620 | 6480 | 0 | 81000
M-LAG | 50715 | 14490 | 1449 | 5796 | 0 | 72450
M-IWG | 28350 | 8100 | 810 | 3240 | 0 | 40500
M-OSG | 66150 | 18900 | 1890 | 7560 | 0 | 94500
M-SSG | 96915 | 27690 | 2769 | 11076 | 0 | 138450
L-ROG | 38538.5 | 27527.5 | 27527.5 | 16516.5 | 0 | 110110
J-TOC | 32400 | 10800 | 5400 | 2700 | 2700 | 54000
J-TSC | 68850 | 22950 | 11475 | 5737.5 | 5737.5 | 114750
Enterprise establishment
Line | Permanent federal | Federal reserve | State / territorial | Certified industry | Partner / allied | Total | Boundary
Direct formations | 680906 | 239845 | 71578 | 77743.5 | 8437.5 | 1078510 | Eleven Pass 23 lines
Allocated institutional overhead | 129421.2 | 0 | 0 | 0 | 0 | 129421.2 | 12% of direct billets, held in permanent federal component
Affiliated enterprise workforce | 810327.2 | 239845 | 71578 | 77743.5 | 8437.5 | 1207931.2 | Crosswalk, not federal employee headcount

## Capital Crosswalk
Capital Crosswalk
Pass 24 decomposes existing Pass 23 WBS lines. Nothing on this sheet is additive to the $12.049T department reference.
Line | Pass 23 source | Source capital $B | Pass 24 allocated $B | Unallocated $B | Treatment | Boundary
A-SMW | Strategic mobility wing | 464 | 464 | 0 | Formation sub-WBS | Asset Build must reconcile to source
A-AAG | Austere air-access group | 167.5 | 167.5 | 0 | Formation sub-WBS | Asset Build must reconcile to source
A-TDG | Tactical distribution group | 324 | 324 | 0 | Formation sub-WBS | Asset Build must reconcile to source
M-POG | Port-opening group | 180 | 180 | 0 | Formation sub-WBS | Asset Build must reconcile to source
M-LAG | Littoral-access group | 138 | 138 | 0 | Formation sub-WBS | Asset Build must reconcile to source
M-IWG | Inland-waterway group | 81 | 81 | 0 | Formation sub-WBS | Asset Build must reconcile to source
M-OSG | Offshore-support group | 315 | 315 | 0 | Formation sub-WBS | Asset Build must reconcile to source
M-SSG | Ocean sustainment group | 639 | 639 | 0 | Formation sub-WBS | Asset Build must reconcile to source
L-ROG | Access and route-opening group | 145.2 | 145.2 | 0 | Formation sub-WBS | Asset Build must reconcile to source
J-TOC | Theater-opening command | 43.2 | 43.2 | 7.1054e-15 | Formation sub-WBS | Asset Build must reconcile to source
J-TSC | Theater sustainment command | 76.5 | 76.5 | 0 | Formation sub-WBS | Asset Build must reconcile to source
Common enabling allocations
Line | Pass 23 source | Source capital $B | Pass 24 allocated $B | Unallocated $B | Treatment | Boundary
3.1 | Non-NUPS bases, depots and ranges | 650 | 600 | 50 | Prepared Network | Four node classes; $50B remains elsewhere
3.2 | Science, technology and proving outside NUPS | 1500 | 220 | 1280 | Innovation Portfolio | Mission-specific R&D share
3.3 | Education and workforce infrastructure | 350 | 120 | 230 | Schools and qualification | Deployment enterprise share
3.4 | Information, forecast and common digital | 400 | 90 | 310 | Movement and asset visibility | Deployment enterprise share
3.5 | Strategic industry and materials outside NUPS | 500 | 350 | 150 | Shipyards, aircraft, rail and critical spares | Deployment enterprise share
Attributable envelope
Measure | Value $B | Treatment | Relationship to Pass 23
Formation capital | 2573.4 | Calculated | Inside $4,942.85B non-NUPS formation line
Common enabling allocation | 1380 | Calculated | Inside five common enabling lines
Pre-reserve attributable capital | 3953.4 | Subtotal | No incremental claim
Attributable program reserve | 790.68 | 20% policy reserve | Part of Pass 23 program reserve
Attributable capital envelope | 4744.08 | Reference | Inside $12,049.02B department capital

## Annual Funding
Twenty-Five-Year Funding Profile
Normalized planning weights phase the attributable enterprise envelope; FY2026 dollars, no escalation or financing assumptions.
Program year | Raw weight | Normalized share | Capital $B | Cumulative $B | Program focus
1 | 1.5 | 1.657% | 78.6312 | 78.6312 | architecture, prototypes and enabling sites
2 | 2 | 2.21% | 104.8415 | 183.4727 | architecture, prototypes and enabling sites
3 | 2.5 | 2.762% | 131.0519 | 314.5246 | architecture, prototypes and enabling sites
4 | 3 | 3.315% | 157.2623 | 471.787 | architecture, prototypes and enabling sites
5 | 4 | 4.42% | 209.6831 | 681.4701 | industrial expansion and serial procurement
6 | 5 | 5.525% | 262.1039 | 943.5739 | industrial expansion and serial procurement
7 | 5.5 | 6.077% | 288.3143 | 1231.8882 | industrial expansion and serial procurement
8 | 6 | 6.63% | 314.5246 | 1546.4128 | industrial expansion and serial procurement
9 | 6.5 | 7.182% | 340.735 | 1887.1478 | industrial expansion and serial procurement
10 | 6.5 | 7.182% | 340.735 | 2227.8829 | industrial expansion and serial procurement
11 | 6.2 | 6.851% | 325.0088 | 2552.8917 | industrial expansion and serial procurement
12 | 5.8 | 6.409% | 304.0405 | 2856.9322 | industrial expansion and serial procurement
13 | 5.4 | 5.967% | 283.0722 | 3140.0043 | fleet completion and network depth
14 | 5 | 5.525% | 262.1039 | 3402.1082 | fleet completion and network depth
15 | 4.5 | 4.972% | 235.8935 | 3638.0017 | fleet completion and network depth
16 | 4 | 4.42% | 209.6831 | 3847.6848 | fleet completion and network depth
17 | 3.5 | 3.867% | 183.4727 | 4031.1575 | fleet completion and network depth
18 | 3 | 3.315% | 157.2623 | 4188.4198 | fleet completion and network depth
19 | 2.5 | 2.762% | 131.0519 | 4319.4717 | fleet completion and network depth
20 | 2.2 | 2.431% | 115.3257 | 4434.7974 | fleet completion and network depth
21 | 1.8 | 1.989% | 94.3574 | 4529.1548 | replacement, reserve and closeout
22 | 1.5 | 1.657% | 78.6312 | 4607.786 | replacement, reserve and closeout
23 | 1.2 | 1.326% | 62.9049 | 4670.6909 | replacement, reserve and closeout
24 | 0.8 | 0.884% | 41.9366 | 4712.6275 | replacement, reserve and closeout
25 | 0.6 | 0.663% | 31.4525 | 4744.08 | replacement, reserve and closeout

## Operating Cost
Mature Annual Operating Screen
Crosswalk to Pass 23 component personnel and O&M assumptions; not an incremental budget claim.
Line | Annual $B | Method | Boundary
Permanent federal personnel | 129.6524 | Workforce × component rate | Includes allocated institutional overhead
Federal reserve personnel | 11.9923 | Workforce × component rate | Readiness and mobilization average
State / territorial personnel | 3.9368 | Workforce × component rate | Combined planning equivalent
Certified industrial force | 6.9969 | Workforce × component rate | Readiness labor; separate enterprise retainer below
Partner / allied support | 0.16875 | Workforce × component rate | U.S. access and exercise support
Formation maintenance and operation | 77.202 | Formation capital × 3% | Fleet and formation screening rate
Common enabling operation | 27.6 | Allocated common capital × 2% | Sites, research infrastructure and industrial tooling
Deployments and enterprise exercises | 25 | Planning allowance | Multi-node closure exercises
Stocks, containers and rotation | 15 | Planning allowance | Mission-configured inventory
Industrial readiness retainers | 15 | Planning allowance | Priority lines, second sources and surge drills
Continuous entry R&T | 12 | Planning allowance | Software, autonomy, materials and field trials
Commercial and partner access | 8 | Planning allowance | Access agreements and capacity assurance
Mature total
Measure | Value $B/year | Meaning
Mature annual operating screen | 332.5491 | Included within the Pass 23 department O&S architecture

## Innovation Portfolio
Deployment and Distribution Technology Frontier
A $220B mission R&D portfolio aimed at bottlenecks no commercial market is likely to solve at required scale.
ID | Technology thrust | 25-year R&D $B | Maturity path | Required advance | Decisive evidence
I01 | Autonomous multimodal load choreography | 32 | R2→R4 | Machine-verifiable load, priority and reroute decisions across air, ship, rail and road | Closed-loop trials with human override and public audit
I02 | Rapid runway and pavement regeneration | 28 | R2→R4 | Robotic assessment, repair materials and high-rate surface restoration | Full-load cycles under heat, flood, debris and aftershock
I03 | Robotic port clearance and hydrography | 24 | R2→R4 | Map, clear, mark and reopen channels and berths without exposing crews | Representative obstruction field and environmental release
I04 | Self-erecting piers and adaptive causeways | 26 | R1→R4 | Bridge ships to damaged shores across tide, sediment and sea-state variation | Structural, fatigue, geotechnical and human-safety proof
I05 | Zero-host-utility responder bases | 22 | R3→R5 | Closed-loop water, energy, thermal, sanitation and waste for large workforces | 30–180 day occupied demonstration
I06 | Resilience intermodal container family | 18 | R2→R5 | Water, oxygen, cold-chain, power, workshop and data modules with common interfaces | Drop, fire, flood, EMI and repeated-transfer qualification
I07 | Distributed cargo aircraft and vertical lift | 30 | R1→R4 | Move high-value modules when roads and runways fail | Airworthiness, lost-link, weather and ground-risk evidence
I08 | Damage-tolerant in-transit visibility | 14 | R3→R5 | Authoritative identity, custody and condition under denied connectivity | Offline reconciliation and cyber-resilience campaign
I09 | Rapid route and bridge digital certification | 12 | R2→R4 | Fuse sensing and engineering to release corridors by load class | Blind validation against instrumented structures
I10 | Reverse-flow hazard logistics | 14 | R2→R5 | Safely move waste, contamination, casualties and damaged energy systems out | End-to-end regulatory and field demonstration
Portfolio reconciliation
Measure | Value | Status | Boundary
R&D allocation | 220 | PASS | Must equal the $220B common-line allocation
Rendering eligibility | 0 | OPEN | No major platform may be rendered from these planning equivalents

## Authority Gates
Authority and Service-Release Gates
Physical throughput cannot substitute for lawful access, safe operation or host acceptance.
Gate | Decision owner | Required record | Failure if absent | Model treatment
Mission invitation / domestic authorization | Secretary + civil authority | Scope, geography, duration and termination | Force arrives without lawful mission | Binary gate; not monetized
Node access | Port, airport, rail, road and land authorities | Access agreement and priority rules | Capacity exists only on paper | Evidence gate
Environmental and public-health release | Technical authority | Sampling, residual, waste and exposure record | Response creates secondary harm | Evidence gate
Structural / air / marine release | Independent safety authority | Load, airworthiness, seaworthiness and operating envelope | Unsafe equipment enters service | Evidence gate
Credential and data governance | Health, utility and privacy authorities | Credential, minimum data and audit policy | Care and services cannot be accepted | Evidence gate
Civil transfer and demobilization | Host authority + inspector general | Acceptance, records, liabilities and residual support | Temporary response becomes unmanaged dependency | Evidence gate

## Failure Modes
Enterprise Failure Modes
Design hazards that a fleet-only approach misses.
ID | Failure mode | Mechanism | Design response | Residual research
F01 | Formation outruns entry | Operating units are prioritized ahead of port, airfield and distribution forces | Entry packages are first-class force elements in every wave | Item-level time-phased trials
F02 | Port is open but cargo stops | Berth clearance is mistaken for end-to-end distribution | Measure node-to-destination throughput and backlog | Live terminal exercises
F03 | Responder force consumes host services | Bases draw damaged water, power, beds and sanitation | Zero-host-utility base modules | Long-duration occupied demonstration
F04 | Single-node optimism | Several nominal nodes share one bridge, grid, channel or labor pool | Independence map and primary-path-loss case | Empirical covariance
F05 | Air urgency becomes air dependence | Low-value heavy cargo crowds out life-safety modules | Effect-based priorities and modal substitution | Load-plan validation
F06 | Prepositioning is inside the hazard | Staged stock is lost with the community it supports | Safe-zone geometry and reversible dispersal | Hazard-specific siting
F07 | Contract capacity is counted twice | The same carrier, driver or mariner appears in multiple plans | Named capacity reservations and readiness exercises | Commercial network audit
F08 | Mariner / operator shortfall | Platforms exist without qualified crews | Permanent, reserve and industrial workforce pipeline | Occupation-level model
F09 | Digital visibility is mistaken for control | Tracking does not create cranes, routes or decisions | Physical capacity and command authority remain separate | D-DIL field trials
F10 | Hazardous reverse flow is omitted | Waste, batteries, fuel, casualties and damaged equipment accumulate | Dedicated reverse-flow packages and facilities | Regulatory design
F11 | The host rejects technically valid service | Standards, records or interfaces do not transfer | Host acceptance designed before deployment | Partner trials
F12 | Maintenance debt is hidden | High tempo consumes future readiness | Reconstitution starts during deployment | Asset-level reset curves
F13 | Fixed hub becomes a regional choke point | Concentration increases correlated loss | Paired hubs, dispersed auxiliaries and mobile nodes | Network interdiction simulations
F14 | Novel autonomy lacks public legitimacy | Safety case and accountability trail are insufficient | Independent release, bounded autonomy and auditability | Human-factors and governance research

## Evidence Gates
Evidence and Maturity Gates
All gates remain open. The workbook establishes design hypotheses, not validated procurement requirements.
ID | Gate | Required evidence | State
E01 | Item-level deployment records | Configuration-controlled people, mass, volume and load compatibility | OPEN
E02 | Wave-to-effect proof | Demonstrate that each wave starts the claimed public service | OPEN
E03 | Aircraft performance | Payload-range, runway, weather, maintenance and airworthiness | OPEN
E04 | Ship performance | Cargo, stability, draft, discharge, crew and lifecycle | OPEN
E05 | Rail / road network | Terminal, bridge, crew, fuel and cycle-time evidence | OPEN
E06 | Inland water network | Draft, river stage, locks, terminals and seasonal limits | OPEN
E07 | Port opening throughput | Hydrography through onward clearance under damage | OPEN
E08 | Airfield opening throughput | Assessment through sustained sortie generation | OPEN
E09 | Route-opening throughput | Survey, clearance, temporary works and traffic control | OPEN
E10 | Responder base endurance | Occupied zero-host-utility demonstration | OPEN
E11 | Sustainment coefficients | Commodity, maintenance, waste, health and reverse flow by formation | OPEN
E12 | Correlated damage | Empirical node and route covariance by hazard | OPEN
E13 | Commercial capacity exclusivity | Named carriers, crews, equipment and priority rights | OPEN
E14 | Workforce occupation model | Training pipeline, retention, rotation and geographic supply | OPEN
E15 | Capital estimate | Engineering WBS, learning curves, schedule and independent cost estimate | OPEN
E16 | Operating estimate | Fuel, labor, maintenance, stock and exercise evidence | OPEN
E17 | Authority and access | Domestic and international decision records exercised | OPEN
E18 | Cyber / D-DIL control | Offline command, reconciliation, safety and recovery | OPEN
E19 | Campaign trials | Ten simultaneous campaigns tested end to end | OPEN
E20 | Rendering release | Engineering configuration, scale and interfaces closed | OPEN

## Sources
Sources and Model Provenance
Primary and official sources inform doctrine and historical constraints; all numerical design values remain explicit assumptions unless noted.
ID | Source | Institution | As of | URL / reference | Use in this model
S01 | JP 4-01, The Defense Transportation System | Joint Chiefs of Staff | 2017 | https://www.jcs.mil/Portals/36/Documents/Doctrine/pubs/jp4_01_20170718.pdf | Integrated transport management, time-phased requirements, JDDOC and JTF-PO
S02 | Universal Joint Task List | Joint Chiefs of Staff | 2026 | https://www.jcs.mil/Portals/36/Documents/Doctrine/training/ujtl_tasks.pdf | Force closure, deployment, JRSOI and required delivery date concepts
S03 | AFI 10-202, Contingency Response Force Operations | Department of the Air Force | 2024 | https://static.e-publishing.af.mil/production/1/af_a3/publication/afi10-202/afi10-202.pdf | Open-airbase force, rapid deployment and D-DIL conditions
S04 | ATP 3-17.2 et al., Airfield Opening | U.S. Army et al. | 2024 | https://static.e-publishing.af.mil/production/1/lemay_center/publication/afttp3-2.68/afttp3-2.68.pdf | Scalable airfield assessment, command, cargo, fuel, medical and maintenance functions
S05 | SDDC Capabilities Book / RPOE | U.S. Army | 2025 | https://api.army.mil/e2/c/downloads/2025/09/10/7a17d558/sddc-capabilities-book.pdf | Rapid port opening, in-transit visibility and initial distribution node
S06 | Response and Recovery Federal Interagency Operational Plan | FEMA | 2025 | https://www.fema.gov/sites/default/files/documents/fema_rd_response-recovery-fiop-npb-042025.pdf | Incident support bases, federal staging areas and resource staging
S07 | Ready Reserve Force | MARAD | 2026 | https://www.maritime.dot.gov/national-defense-reserve-fleet/ndrf/maritime-administration%E2%80%99s-ready-reserve-force | Reserve activation, outporting, crew and surge-sealift functions
S08 | GAO-07-807, Defense Logistics | Government Accountability Office | 2007 | https://www.gao.gov/products/gao-07-807 | Consequences of delaying port-opening forces and limits of isolated opening units
S09 | GAO-17-503, Navy Readiness | Government Accountability Office | 2017 | https://www.gao.gov/products/gao-17-503 | Aging sealift, readiness decline and capital-planning requirements
S10 | GAO-21-125, Defense Transportation | Government Accountability Office | 2021 | https://www.gao.gov/products/gao-21-125 | Mobility studies, contested training and sealift readiness
S11 | National Emergency Preparedness Program | U.S. Army Corps of Engineers | current | https://www.usace.army.mil/Missions/Emergency-Operations/National-Response-Framework/Emergency-Power/ | Emergency engineering, debris, power and infrastructure missions
S12 | Joint Force Allocation Model | Disaster Force Pass 23 | 2026-09-04 | models/joint-force-allocation-model.xlsx | Campaign mass, people, sustainment, formations, workforce and capital baseline

## Checks
Model Checks
PASS means the declared relationship holds; it does not validate the assumptions. OPEN is intentional uncertainty.
ID | Check | Result | Interpretation
C01 | Ten campaigns present | PASS | Portfolio scope
C02 | Campaign wave shares equal 100% | PASS | Each campaign closes at 100%
C03 | Mode shares equal 100% | PASS | No mass invented or omitted
C04 | All movement deadlines close | PASS | Four modes × four deadlines
C05 | Node allocations fit availability credit | PASS | Ten-campaign simultaneous allocation
C06 | All reference reception chains close | PASS | 14-day reception
C07 | All reference onward chains close | PASS | Staging and onward movement
C08 | All reference responder bases close | PASS | No host-service draw
C09 | All reference sustainment chains close | PASS | Daily flow
C10 | All reference end-to-end chains close | PASS | Weakest-link rule
C11 | Exactly eight degraded chains close | PASS | Cascadia and allied megacity remain short
C12 | Force capital matches asset build | PASS | Formation sub-WBS
C13 | Prepared network equals $600B | PASS | Inside Pass 23 common bases line
C14 | Innovation portfolio equals $220B | PASS | Inside Pass 23 R&D line
C15 | Capital reserve equals 20% | PASS | Explicit reserve
C16 | Funding shares equal 100% | PASS | Twenty-five program years
C17 | Funding ties to attributable envelope | PASS | No capital lost in phasing
C18 | Workforce direct total matches force lines | PASS | No billet double count
C19 | Mature operating screen is positive | PASS | Crosswalk only
C20 | All evidence gates remain open | OPEN | No validation claim
C21 | Rendering remains blocked | OPEN | User-directed sequencing